## Sheet1
S.No | Date | Module | Particular | Solution | Status | Remarks
64 | 2017-11-16 | Inventory | New Reports Required---Stock balance reports with PO number |  | PENDING
67 | 2017-11-16 | Accounts | Please verify the account entry and reports(Like payment, TDS,GST) |  | PENDING
72 | 2017-12-13 | Production | Display Reports is required in detail for the job receive |  | Incomplete
74 | 2017-12-13 | Inventory | Stock balance, stock in hand & stock in process display reports are not complete |  | Incomplete
75 | 2017-12-13 | Inventory | New inventory reports required with value for the account |  | Incomplete | I have sent the format sheet
78 | 2018-01-15 | SALE | Sale Order Amendment |  | Incomplete
80 | 2018-01-15 | Production | Display Reports is required in detail for the job invoice |  | PENDING
82 | 2018-01-16 | SALE | New reports of packed goods to be sale, po & item wise summery |  | PENDING
84 | 2018-01-17 | Production | Bedding Set entry process |  | Incomplete
86 | 2018-02-01 | production | Rate are not correct in job invoice reports list |  | PENDING
89 | 2018-02-01 | Purchase | Additional charge option in Purchase invoice return for freight charge & other charge |  | PENDING
94 | 2018-02-02 | PLANNING | Production plan cancel entry point are not working in proper way |  | Incomplete
96 | 2017-02-06 | Product | There is no option to print of item list, job worker list & supplier list |  | Incomplete
97 | 2017-02-06 | SALE | There is not process wise reports in sale enquiry. |  | PENDING
99 | 2017-02-06 | Purchase | Editing is not working properly in purchase return challan |  | PENDING
102 | 2018-03-08 | Purchase | Item, dimension & rate wise summery copy of Purchase order |  | PENDING
105 | 2018-03-09 | Product | Process wise raw material cost of single item |  | PENDING
106 | 2018-03-09 | Planning | Process wise raw material cost against planning ---Reports |  | PENDING
107 | 2018-03-09 | Planning | Production plan status report with correct dimensions |  | PENDING
108 | 2018-03-09 | Planning | Purchase plan status report with correct dimensions |  | PENDING
109 | 2018-04-07 | Purchase | Product Purchase history--- need to dimension wise reports |  | Incomplete
110 | 2018-04-07 | SALE | Sale order balance reports should be as per entry serial number |  | PENDING
111 | 2018-04-07 | Production | Stock in process reports are showing in minus due to fabric dimension in perk |  | PENDING
112 | 2018-04-07 | Product | Sale tax group not pick at the time of item master list import |  | PENDING
113 | 2018-04-07 | Product | Sate tax group to be corrected of barcode item |  | PENDING
114 | 2018-04-08 | Purchase | Purchase return invoice--- Total value after round off not posting on purchase invoice. |  | PENDING
115 | 2018-04-08 | Product | Process wise material link for process wise material planning. |  | PENDING
116 | 2018-04-25 | Inventory | There is no godown filter in internal process reports |  | PENDING
117 | 2018-04-25 | Inventory | Lot number not print in material issue slip |  | PENDING
118 | 2018-04-25 | Inventory | Lot number not pick when material issue from for stock-in |  | PENDING
119 | 2018-04-25 | Inventory | Lot number not pick when material return from job from for issue |  | PENDING
120 | 2018-04-25 | Inventory | Lot number not pick when store issue from for stock-in |  | PENDING
121 | 2018-05-04 | Production | Job order status report is not working for repair process with details filter |  | PENDING